## Sheet1
ID | Title | Work Item Type | State | Effort | Iteration Path | Tags
361 | Move File Size, Type Constraints Variables to the Web Configuration | Product Backlog Item | New |  | RACApplication
359 | RAC Advisor - Manage Competancies / Programs | Product Backlog Item | New |  | RACApplication
331 | Make Model changes on database | Product Backlog Item | Committed | 20 | RACApplication\Release 2\Sprint 2
41 | RAC Advisor - View RAC Requests + Candidates | Product Backlog Item | Committed | 8 | RACApplication\Release 2\Sprint 2
37 | RAC Advisor - Archive/Delete Accounts | Product Backlog Item | Committed | 3 | RACApplication\Release 2\Sprint 2
321 | RAC Advisor - Ability to Comment on RAC Request Self Evaluation | Product Backlog Item | New |  | RACApplication\Release 2
323 | Investigate and Implement School and Microsoft Standards for Password | Product Backlog Item | Committed | 5 | RACApplication\Release 2\Sprint 2
47 | Show Change Notifications from Candidates | Product Backlog Item | Committed | 10 | RACApplication\Release 2\Sprint 2
316 | Candidate Flow - Fix Issues from Sprint 1 | Product Backlog Item | Committed | 5 | RACApplication\Release 2\Sprint 2
348 | Enhance Code Unit Test Coverage Percentage | Product Backlog Item | Committed | 10 | RACApplication\Release 2\Sprint 2
360 | Add Privacy Policy Acceptance Checkbox + Text to the Account Registration Page | Product Backlog Item | New |  | RACApplication
43 | RAC Advisor - Modify a Candidate's RAC Requests | Product Backlog Item | New |  | RACApplication
45 | RAC Advisor - Delete a Candidate's RAC Requests | Product Backlog Item | New |  | RACApplication
319 | Make System Mobile Friendly | Product Backlog Item | Committed | 10 | RACApplication\Release 2\Sprint 2
362 | System Security Audit | Product Backlog Item | New |  | RACApplication
303 | CSS Files Do Not Follow a Naming Standard | Bug | New | 1 | RACApplication | refactor
294 | JavaScript Files Do Not Follow a Naming Standard | Bug | New | 1 | RACApplication | refactor
31 | RAC Advisor - Create Candidate Accounts | Product Backlog Item | New | 13 | RACApplication\Release 2
222 | Rewrite Account Controller Unique Email | Product Backlog Item | New | 2 | RACApplication | refactor
243 | Rewrite Unique Email Verification as a service method | Task | Removed |  | RACApplication
307 | Remove Web API packages | Bug | New |  | RACApplication
356 | Create Login for Content Specialist | Product Backlog Item | New |  | RACApplication
128 | Get Login Working for All Users | Product Backlog Item | Committed |  | RACApplication
308 | Legal consent for protected information interface | Product Backlog Item | New |  | RACApplication
314 | RAC Advisor - Add a Content Specialist | Product Backlog Item | New |  | RACApplication
313 | RAC Advisor - View Content Specialists | Product Backlog Item | New |  | RACApplication
53 | RAC Advisor - Refer Request to Content Specialist | Product Backlog Item | New |  | RACApplication
317 | Content Specialist - Sign In | Product Backlog Item | New |  | RACApplication
61 | Content Specialist - Submit Evaluated RAC Request | Product Backlog Item | New |  | RACApplication
59 | Content Specialist - See Candidates Documentation | Product Backlog Item | New |  | RACApplication